## Sheet1
Tasks | Start date | End date | Who? | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Phase 1:
Project planning | Jan.2025 | March.2025
User requirements | March.2025 | April.2025
System selection | May.2025 | September.2025
System configuration | June.2025 | September.2025
Data Migration | September.2025 | December.2025
Phase 2:
Staff training | December.2025 | March.2026
Launch the system | March.2026 | March.2026
Post-implementation support | April.2026 | Ongoing